5-Year State Plan Timeline

March 2015:   				DD Council Approve Timeline

April through August 2015:  		Needs Assessments

- Statewide

  - People First Organizations

  - Public Aware Collaboration Events (PACE)

  - Employment Summit Information

August 2015:				DD Evaluation Committee Meeting

- Utilizing Data Collected Develop 5-Year State Plan for Recommendation to DD Council

September 2015:			Face-to-Face DD Council Meeting

- Discussion/Approval of 5-Year State Plan Recommendation

October 2015:   	Executive Director Complete 5-Year State Plan Draft for Public Comment

November 2015:	DD Evaluation Committee Meeting

- Finalization of Draft to present to DD Council

For Approval to go forward for Public Comment

December 2015:			DD Council Meeting Approval of Draft

January & February 2016:		Public Comment

- People First

- Statewide Town Hall Meetings

Include:

- Multiple Rural Locations

- Native American

February 2016:			DD Evaluation Committee Meeting

- Review of Public Comments to determine if modifications are needed

March 2016:				Face-to-Face DD Council Meeting

- Council will approve the Final Plan

April 2016:				“If needed” go back out for Public Comment

May 2016				“If needed” DD Evaluation Committee Meeting

June 2016:				“If needed” Face-to-Face DD Council Meeting