**Timeline of New 5-Year State Plan**

**May 2024 – January 2025 –** Town halls and gathering input

**February 2025 – May 2025 –** Writing Draft 5 Year State Plan, review and input from Executive Committee

**June 2025 Council Meeting –** 1st Draft review by full Council

**July 2025 –** Release draft to the public and begin 1st 45-day public comment period.

**September 2025 Council Meeting –** Review any comments. Consider implementing comments. If substantive changes are made, release for another 45 day public comment period. If no changes are made, approve the 5-Year State Plan, and release it to the public.

**December 2025 Council Meeting –** Review new 5 Year State Plan and any potential comments. The Council will review any new comments from 2nd 45-day public comment period. Comments can be approved and implemented. If any substantive changes are made, release for another 45-day public comment period. If no changes are made, approve the 5-Year State Plan, and release it to the public.